## Sheet1
NAIT Tech Migration Project - Sample Budget
Prepared by Chris Redford | [5 empty] | This Spreadsheet needs to be modified to fit your project details, add / remove items and if you cannot get get the formulas to work for you ask for assistance
Prepared by Chris Redford | # Units/Hrs. | Cost/Unit/Hr. | Subtotals | Category Total | % of Total
Project Management Staff |  |  |  | 250000 | 22.7%
Project manager | 960 | 100 | 96000
Project team members | 1920 | 75 | 144000
Contractors (Cabling, Software Customization) | 100 | 100 | 10000
Hardware
Network Infrastructure |  |  |  | 80000 | 7.263%
Routers | 3 | 5000 | 15000
L2 Switches | 6 | 4000 | 24000
L3 Switches | 3 | 6000 | 18000
Edge Firewall | 1 | 8000 | 8000
Site Firewalls | 3 | 3000 | 9000
Racks, Cable, Accessories | 1 | 6000 | 6000
Server Infrastructure |  |  |  | 206000 | 18.7%
Blade Servers + Chassis | 2 | 60000 | 120000
Drive Array + Drives | 2 | 40000 | 80000
Racks, Cable, Accessories | 1 | 6000 | 6000
Client Infrastructure |  |  |  | 382500 | 34.72%
PC Users - PC + 2 Monitors | 175 | 1500 | 262500
Mobile Users - Laptop + Extra Monitor + Docking Station | 65 | 1200 | 78000
Tablet Users - MS Surface + 1 Hand Cases | 35 | 1200 | 42000
Software
Licensing |  |  |  | 94625 | 8.59%
On-Prem Operating Systems - Windows 2019 Standard | 10 | 1000 | 10000
On-Prem Operating Systems - Windows 10 Pro | 275 | 175 | 48125
Microsoft 365 Premium Licensing | 275 | 100 | 27500
Misc Software Licensing (Adobe, Winzip, Database) | 1 | 9000 | 9000
Cloud Access / Licensing / Data Storage |  |  |  | 18000 | 1.634%
AWS | 1 | 9000 | 9000
Azure | 1 | 9000 | 9000
Construction / Renovation |  |  |  | 12000 | 1.089%
Labour | 40 | 100 | 4000
Materials | 1 | 8000 | 8000
Training and Support |  |  |  | 58400 | 5.302%
IT Skills Training | 100 | 500 | 50000
User Training | 12 | 700 | 8400
Reserves |  |  |  | 165228.75 | 15%
Contingency Reserves (Known Unknowns) 10% |  |  | 110152.5
Management Reserves (Unknown unknowns) 5% |  |  | 55076.25
Total Project Cost Estimate - Does Not Include Reserves |  |  |  | 1101525